## Title
『NEW HRM 』
Development Schedule
2020-07-01

## History Update
UPDATE HISTORY
Version | Date | Description | Author
1.0 | 2020-07-01 | First draft schedule | Nguyen Hue
1.1 | 2020-07-29 | Change schedule | Nguyen Hue
1.2 | 2020-08-24 | Update schedule | Nguyen Hue

## Schedule
[NEW HRM] SYSTEM
Author | Nguyen Thi Hue |  |  |  |  | # | Resource | Time in Project
Date | 2020-07-30 |  |  |  |  | 1 | Nguyễn Thị Huệ | 100%
Platform | MS C# ASP.NET VS 2015 Community |  |  |  |  | 3 | Nguyễn Duy Hưng | 100%
Database | My SQL, MS SQL Server,Oracle 11g |  |  |  |  | 4 | Đỗ Xuân Dũng | 100%
Libraries | DevExpress ASP.NET MVC, Reporting |  |  |  |  | 5 | Hoàng Trung Hiếu | 100%
[6 empty] | 6 | Trần Văn Việt | 100%
Expected finished date: | 2020-12-12 |  |  |  |  | 7 | Lê Ngọc Tuấn | 100% | Time line | 1 |  |  | Plan Begin | [5 empty] | Actual Begin |  |  |  |  | % Completed |  |  |  | Actual (Out of plan) | [5 empty] | % Completed (Out of plan)
[10 empty] | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU | 2 | 3 | 4 | 5 | 6 | 7 | SU
# | Form Name | Funtions | Description | Resource | Plan Begin | Plan Duration | Actual Begin | Actual Duration | % Completed | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan
 | time axis 2020-07-30 to 2021-01-24
 | time axis 2020-07-30 to 2021-01-24
GRAND COUNT |  | 254
PREPARE |  | 7
Database | Maria DB | Create | Ms.Sri |  | 1 | 5 | 2 | 1
Framwork | New Framwork | Framwork separate layer with each mission and inheritance | Create new framwork. | Đỗ Xuân Dũng | 1 | 8 | 1 | 8
Stype defind | Theme using, icon find |  |  | Nguyễn Duy Hưng | 1 | 8 | 1 | 8
Document | Document | Collect document, Database design |  | Nguyễn Thị Huệ | 1 | 8 | 1 | 8
Paging | Paging function | Create paging function using for all of form |  | Đỗ Xuân Dũng | 9 | 4 | 9 | 4
Dictionary loading | Create function loading dictionary |  |  | Nguyễn Duy Hưng | 9 | 5 | 9 | 5
Model form | Model code help | Create model code help form |  | Nguyễn Duy Hưng | 14 | 15
Procedure excute method | Procedure excute method in code | Procedure excute method in code |  | Đỗ Xuân Dũng | 9 | 8 | 9 | 8
Region function | Create region function | Usng json load data |  | Hoàng Trung Hiếu | 19 | 10
CONFIGURATION |  | 23
FrmSYFform | FORM | Insert, Update, Delete |  | Hoàng Trung Hiếu | 29 | 3
|  | Dictionary |  | Hoàng Trung Hiếu | 29 | 3
FrmSYMmenu | MENU | Insert, Update |  | Hoàng Trung Hiếu | 33 | 6
|  | Active, InActive, Dictionary |  | Hoàng Trung Hiếu | 33 | 6
FrmSYCcategory | CATEGORY | Insert, Update | Add or Update data | Hoàng Trung Hiếu | 40 | 6
|  | Active, InActive, Dictionary | Don't using delete data, Add dictionary field | Hoàng Trung Hiếu | 40 | 6
|  | Admin or User | Some category can be open for user | Hoàng Trung Hiếu | 40 | 6
FrmSYSDdictionary | DICTIONARY | Insert, Update | Add or Update data
|  | Active, InActive | Don't using delete data
|  | Admin or User | Some category can be open for user
|  | Menu, Form, Control | Apply for all title, control
FrmSYSRreport | REPORT CONFIG | Insert, Update | Add or Update data | Hoàng Trung Hiếu | 46 | 7
|  | Configuration report name, link, dictionary, active, inactive, parameter | Configuration report | Hoàng Trung Hiếu | 46 | 7
|  | Authorization | Authorization user | Hoàng Trung Hiếu | 46 | 7
FrmSYUuser | USER | Insert, Update | Add or Update data | Đỗ Xuân Dũng | 40 | 6
|  | Active, Inactive | Don't using delete data | Đỗ Xuân Dũng | 40 | 6
|  | Role selected | Selected role | Đỗ Xuân Dũng | 40 | 6
|  | Organization selected | Selected Organization | Đỗ Xuân Dũng | 40 | 6
|  | Company selected |  | Đỗ Xuân Dũng | 40 | 6
FrmSYAauthorization | AUTHORIZATION | Setup authentication & Authorization |  | Đỗ Xuân Dũng | 19 | 5 | 19 | 5
|  | Create Login form |  | Đỗ Xuân Dũng | 26 | 4
|  | Form selected |  | Đỗ Xuân Dũng | 30 | 6
|  | Insert, Update, Delete, Report, Export choose |  | Đỗ Xuân Dũng | 36 | 2
H/R INFORMATION |  | 74
FrmHRBbasicinfo | HR BASIC INFORMATION | Basic UI and control using |  | Nguyễn Thị Huệ | 9 | 8 | 9 | 8
|  | Model data loading |  | Nguyễn Thị Huệ | 17 | 4 | 17 | 4
|  | Update personal info |  | Nguyễn Thị Huệ | 26 | 3
|  | Update work info |  | Nguyễn Thị Huệ | 26 | 3
|  | Add, Update certification |  | Nguyễn Thị Huệ | 29 | 3
|  | Add, Update family info |  | Nguyễn Thị Huệ | 21 | 3 | 21 | 3
|  | View discipline |  | Nguyễn Thị Huệ | 32 | 2
|  | View skill |  | Nguyễn Thị Huệ | 32 | 2
|  | Basic info history |  | Nguyễn Thị Huệ | 26 | 3
|  | Work history before join in |  | Nguyễn Thị Huệ | 34 | 4
FrmHROorganization | ORGANIZATION | Add, Update department |  | Lê Ngọc Tuấn | 26 | 6
|  | Active, Inactive note |  | Lê Ngọc Tuấn | 26 | 6
|  | Sort by view mode |  | Lê Ngọc Tuấn | 26 | 6
FrmHRCcompanyinfo | COMPANY INFO | Add, update company info |  | Lê Ngọc Tuấn | 32 | 7
|  | Data contract (labor contract print) |  | Lê Ngọc Tuấn | 32 | 7
|  | Print information (Report print) |  | Lê Ngọc Tuấn | 32 | 7
FrmHRWworkingstatus | OFFICIAL ORDER (WORKING STATUS) | Add, update working status |  | Nguyễn Thị Huệ | 39 | 6
|  | Confirm to update newest in Basic info. |  | Nguyễn Thị Huệ | 39 | 6
|  | Can not change data after confirmed |  | Nguyễn Thị Huệ | 39 | 6
FrmHRLlaborcontract | ENTER LABOR CONTRACT | Add, update labor contract |  | Lê Ngọc Tuấn | 39 | 6
|  | Confirm to update newest in Basic info. |  | Lê Ngọc Tuấn | 39 | 6
|  | Can not change data after confirmed |  | Lê Ngọc Tuấn | 39 | 6
|  | Print template by format (PDF, word) |  | Lê Ngọc Tuấn | 39 | 6
FrmHRLNextcontract | NEXT LABOR CONTRACT | Review current labor contract and Next labor contract |  | Lê Ngọc Tuấn | 45 | 7
|  | Edit to change data next contract and saving |  | Lê Ngọc Tuấn | 45 | 7
|  | Delete next contract info and make again information. |  | Lê Ngọc Tuấn | 45 | 7
|  | Transfer to labor contract table after saving |  | Lê Ngọc Tuấn | 45 | 7
FrmHRDdisciplineinput | DISCIPLINE BATH INPUT | Show the list employee by department |  | Nguyễn Thị Huệ | 45 | 7
|  | Create data after fill out information and choose emp |  | Nguyễn Thị Huệ | 45 | 7
|  | Query result data |  | Nguyễn Thị Huệ | 45 | 7
FrmHRDdisciplineconf | DISCIPLINE CONFIGURATION | Add ,update, delete deduct of discipline condition |  | Nguyễn Thị Huệ | 52 | 7
|  | Select salary item (evalauation or salary table) by period |  | Nguyễn Thị Huệ | 52 | 7
FrmHRSskillinput | SKILL BATH INPUT | Show the list employee by department |  | Nguyễn Thị Huệ | 59 | 6
|  | Create data after fill out information and choose emp |  | Nguyễn Thị Huệ | 59 | 6
|  | Query result data |  | Nguyễn Thị Huệ | 59 | 6
FrmHRSskillconf | SKILL CONFIGURATION | Add, update,delete condition skill result |  | Nguyễn Thị Huệ | 65 | 5
|  | Based on question test write down score |  | Nguyễn Thị Huệ | 65 | 5
FrmHRSskilltesting | SKILL TESTING | Select question combo and employee to test. |  | Nguyễn Thị Huệ | 70 | 12
|  | Allocation employee with test content => saving |  | Nguyễn Thị Huệ | 70 | 12
|  | Print template testing with question list |  | Nguyễn Thị Huệ | 70 | 12
|  | Input score test and get back result => skill result |  | Nguyễn Thị Huệ | 70 | 12
|  | Confirm to update empoyee skill |  | Nguyễn Thị Huệ | 70 | 12
FrmHRRrecruitmentrequest | RECRUITMENT REQUEST | Add, update plan reccuitment of each department |  | Lê Ngọc Tuấn | 52 | 5
|  | Query result with condition |  | Lê Ngọc Tuấn | 52 | 5
FrmHRRcandidateapply | CANDIDATE APPLY | Add, Update candidate information |  | Lê Ngọc Tuấn | 57 | 5
|  | Accept recruitment after pass test |  | Lê Ngọc Tuấn | 57 | 5
|  | Create employee ID after recruitment offer (add data on HR basic info) |  | Lê Ngọc Tuấn | 57 | 5
FrmHRRcandidateappointment | CANDIDATE APPOINTMENT | Query list of candidate by request |  | Lê Ngọc Tuấn | 62 | 5
|  | Select candidate and fill out date interview, place and saving. |  | Lê Ngọc Tuấn | 62 | 5
|  | Remove data and adding if something change |  | Lê Ngọc Tuấn | 62 | 5
FrmHRTtraningCourse | TRAINING COURSE REGISTER | Add, Update, delete source training |  | Lê Ngọc Tuấn | 67 | 5
|  | Set active, Inactive |  | Lê Ngọc Tuấn | 67 | 5
FrmHRTtrainingSelect | TRAINING SELECT | Select course |  | Lê Ngọc Tuấn | 72 | 5
|  | Update more detail course for training |  | Lê Ngọc Tuấn | 72 | 5
|  | Select list of employee to training |  | Lê Ngọc Tuấn | 72 | 5
|  | Save to apply |  | Lê Ngọc Tuấn | 72 | 5
FrmHRTtrainingResult | TRAINING RESULT | Choose sourse selected |  | Lê Ngọc Tuấn | 77 | 12
|  | Choose file path of scores emplyee |  | Lê Ngọc Tuấn | 77 | 12
|  | Upload to view on grid, User can be change scores again |  | Lê Ngọc Tuấn | 77 | 12
|  | Submit to save data |  | Lê Ngọc Tuấn | 77 | 12
|  | Click result to finished course |  | Lê Ngọc Tuấn | 77 | 12
FrmHRVenderInfo | VENDER INFO. | Add, Update, Delete vender information |  | Nguyễn Thị Huệ | 82 | 3
FrmHRVNewEmpRegister | REGISTER NEW EMPLOYEE | Add, Update, Delete new employee of vender. |  | Nguyễn Thị Huệ | 85 | 6
|  | Create employee ID and transfer to HR basic information |  | Nguyễn Thị Huệ | 85 | 6
FrmHRQuestionCategory | QUESTION CATEGORY | Create structure question (hierarchy) |  | Nguyễn Thị Huệ | 91 | 3
|  | Base on question type make category ID and parent. |  | Nguyễn Thị Huệ | 91 | 3
|  | Active, inactive item using |  | Nguyễn Thị Huệ | 91 | 3
FrmHRQuestionInfo | QUESTION INFO. | Create list of question base on question category |  | Nguyễn Thị Huệ | 94 | 5
|  | Update, Delete function |  | Nguyễn Thị Huệ | 94 | 5
|  | Active, inactive item using |  | Nguyễn Thị Huệ | 94 | 5
|  | Query data result |  | Nguyễn Thị Huệ | 99 | 5
FrmHRQuestionSet | QUESTION SET | Query structure of category question and choose version |  | Nguyễn Thị Huệ | 99 | 5
|  | Add question on the structure question type |  | Nguyễn Thị Huệ | 99 | 5
|  | Remove question out structure |  | Nguyễn Thị Huệ | 99 | 5
TIME SHEET |  | 45
FrmTSWorkTime | WORK TIME | Add, Update work time |  | Nguyễn Duy Hưng | 29 | 5
|  | Configuration on department, employee |  | Nguyễn Duy Hưng | 29 | 5
FrmTSTimeShift | TIME SHIFT | Add, Update shift using |  | Nguyễn Duy Hưng | 34 | 3
|  | Active, Inactive apply |  | Nguyễn Duy Hưng | 34 | 3
FrmTSHoliiday | HOLIDAY | Add, Update holiday |  | Nguyễn Duy Hưng | 37 | 5
|  | Configuration by department |  | Nguyễn Duy Hưng | 37 | 5
FrmTSWorkshift | REGISTER WORK SHIFT | Register work shift for employee work diffirent in configuration |  | Nguyễn Duy Hưng | 42 | 10
|  | Option choose the date apply (case change date) |  | Nguyễn Duy Hưng | 42 | 10
|  | Can be more than 1 shift on day |  | Nguyễn Duy Hưng | 42 | 10
|  | Confirm data |  | Nguyễn Duy Hưng | 42 | 10
FrmTSAbsenceRegister | ABSENCE REGISTER | Register, update, delete absence by employee, department |  | Nguyễn Duy Hưng | 52 | 16
|  | Batch input data |  | Nguyễn Duy Hưng | 52 | 16
|  | Confirm data |  | Nguyễn Duy Hưng | 52 | 16
|  | Open functions to apply in smartphone | APP | Nguyễn Duy Hưng | 52 | 16
|  | Check absence status in smartphone | APP | Nguyễn Duy Hưng | 52 | 16
FrmTSDailyWorkConfirm | DAILY WORK CONFIRM | Log data finger to compare with shift and show result |  | Nguyễn Duy Hưng | 68 | 19
|  | Link to absence, holiday to daily work |  | Nguyễn Duy Hưng | 68 | 19
|  | Display work data with more than 1 shift |  | Nguyễn Duy Hưng | 68 | 19
|  | Show work data in case change date work |  | Nguyễn Duy Hưng | 68 | 19
FrmTSDailyWorkByPerson | DAILY WORK BY PERSON | Show on work recored of employee in month |  | Nguyễn Duy Hưng | 87 | 6
|  | Print template attendance by person on month |  | Nguyễn Duy Hưng | 87 | 6
FrmTSOverTimeConfig | OVER TIME CONFIGURATION | Add, update time and kind of over time by shift | Using for auto | Hoàng Trung Hiếu | 53 | 6
|  | Confirm data |  | Hoàng Trung Hiếu | 53 | 6
FrmTSOverTimePlan | OVER TIME PLAN | Regitser OT plan for employee |  | Hoàng Trung Hiếu | 59 | 6
|  | Batch input data support |  | Hoàng Trung Hiếu | 59 | 6
|  | Accept function |  | Hoàng Trung Hiếu | 59 | 6
FrmTSOverTimeConfirm | OVER TIME CONFIRM | Base on daily work and OT plan or configuration, log OT data | If Plan > Actual, Actual, plan | Hoàng Trung Hiếu | 65 | 12
|  | Check one or more record |  | Hoàng Trung Hiếu | 65 | 12
|  | Confirm data |  | Hoàng Trung Hiếu | 65 | 12
|  | Link from OT plan, if not then link from configuration |  | Hoàng Trung Hiếu | 65 | 12
FrmTSLeaveConfiguration | LEAVE CONFIGURATION | Add condition for leave calculate with each kind of leave |  | Hoàng Trung Hiếu | 77 | 5
|  | Formula calculate remain leave |  | Hoàng Trung Hiếu | 77 | 5
FrmTSLeaveManagement | LEAVE MANAGEMENT | Show information employee with leave data. |  | Hoàng Trung Hiếu | 82 | 5
|  | Display the used date and remain base on configuration | Already annual leave function | Hoàng Trung Hiếu | 82 | 5
FrmTSLeaveTransfer | LEAVE TRANSFER | Show all of leave result |  | Hoàng Trung Hiếu | 87 | 5
|  | Check date remain and choose Pay type, Month to save | None, Payment, transfer | Hoàng Trung Hiếu | 87 | 5
|  | Confirm data | Already annual leave function | Hoàng Trung Hiếu | 87 | 5
FrmTSTimeSheetItem | TIMESHEET ITEM | Add, Update timesheet items |  | Nguyễn Duy Hưng | 93 | 5
|  | Choose option for absence, Over time,… |  | Nguyễn Duy Hưng | 93 | 5
FrmTSTimeSheetFormulated | TIMESHEET FORMULATED | Add configuration for formuated item |  | Nguyễn Duy Hưng | 98 | 12
|  | Option to change on future |  | Nguyễn Duy Hưng | 98 | 12
FrmTSTimeSheetResult | TIMESHEETRESULT | Function to calutate timesheet on month |  | Nguyễn Duy Hưng | 110 | 12
|  | Base on department and version salary |  | Nguyễn Duy Hưng | 110 | 12
|  | Confirm data |  | Nguyễn Duy Hưng | 110 | 12
|  | Function closing data |  | Nguyễn Duy Hưng | 110 | 12
SALARY/BONUS |  | 43
FrmPRsalaryVersion | SALARY VERSION | Add, Update salary version | Advance, salary, bonus | Trần Văn Việt | 26 | 5
|  | Add the department is condition |  | Trần Văn Việt | 26 | 5
|  | The period timesheet closing |  | Trần Văn Việt | 26 | 5
FrmPRsalaryTable | SALARY TABLE | Base on salary version make salary table by Job Code |  | Trần Văn Việt | 31 | 7
|  | Calculate on each step, level ,salary |  | Trần Văn Việt | 31 | 7
|  | Save to apply |  | Trần Văn Việt | 31 | 7
FrmPRsalaryItem | SALARY ITEMS | Create salary items for each type and resource to link data |  | Trần Văn Việt | 38 | 7
|  | Condition to link data result | configuration, upload, input,… | Trần Văn Việt | 38 | 7
|  | Active, Inactive apply |  | Trần Văn Việt | 38 | 7
FrmPRcalculateMethod | CALCULATION METHOD | Choose item salary.Add, update condition to take amount |  | Trần Văn Việt | 45 | 9
|  | Set by amount, rate with period apply |  | Trần Văn Việt | 45 | 9
FrmPRsalaryFormulate | SALARY FORMULATED | Choose item salary.Add each formulated |  | Trần Văn Việt | 54 | 12
|  | View salary formulated total |  | Trần Văn Việt | 54 | 12
FrmPRAdvancePayment | ADVANCE PAYMENT | Query advance payment data |  | Lê Ngọc Tuấn | 89 | 12
|  | Save advance payment data with kind and method | Mehtod: formulated or amount input | Lê Ngọc Tuấn | 89 | 12
|  | Confirm advance payment data |  | Lê Ngọc Tuấn | 89 | 12
FrmPREnterAllowance | ENTER ALLOWANCE | Add, update delete allowance by each employee | Insace some employee allowance not same in configuration | Lê Ngọc Tuấn | 101 | 7
|  | Query result |  | Lê Ngọc Tuấn | 101 | 7
FrmPRUploadPaymentData | UPLOAD PAYMENT DATA | Choose department, Item for query result. |  | Lê Ngọc Tuấn | 108 | 6
|  | Choose file path for upload data |  | Lê Ngọc Tuấn | 108 | 6
|  | Submit to save data |  | Lê Ngọc Tuấn | 108 | 6
FrmPRCalculatedSalary | CALCULATE SALARY | Choose department, version, month to calculate salary |  | Trần Văn Việt | 66 | 19
|  | Calculate function by department or person |  | Trần Văn Việt | 66 | 19
|  | Cancel function |  | Trần Văn Việt | 66 | 19
|  | Review data function click |  | Trần Văn Việt | 66 | 19
FrmPRbonusSetting | BONUS SETTING | Choose version, department to review data |  | Trần Văn Việt | 85 | 5
|  | Add, Update, Delete bonus condition |  | Trần Văn Việt | 85 | 5
FrmPRbonusCaculate | CALCULATE BONUS | Choose department, version, month to calculate bonus |  | Trần Văn Việt | 90 | 12
|  | Calculate function by department or person |  | Trần Văn Việt | 90 | 12
|  | Cancel function |  | Trần Văn Việt | 90 | 12
|  | Review data function click |  | Trần Văn Việt | 90 | 12
FrmPRSalaryReport | SALARY REPORT | View result of salary calculate |  | Trần Văn Việt | 102 | 5
|  | Re-calculate for each employee |  | Trần Văn Việt | 102 | 5
|  | Closing salary data |  | Trần Văn Việt | 102 | 5
FrmPRBonusReport | BONUS REPORT | View result of bonus calculate |  | Trần Văn Việt | 107 | 5
|  | Adjust bonus data |  | Trần Văn Việt | 107 | 5
|  | Closing bonus data |  | Trần Văn Việt | 107 | 5
|  | Print bonus report |  | Trần Văn Việt | 107 | 5
FrmPRsalaryClosing | SALARY CLOSING | Choose department, month to closing |  | Trần Văn Việt | 112 | 5
|  | View history closing |  | Trần Văn Việt | 112 | 5
FrmPRSendPayslip | SEND PAYSLIP | View payslip data |  | Trần Văn Việt | 117 | 10
|  | Choose function send payslip | Email, SMS | Trần Văn Việt | 117 | 10
|  | Show result send |  | Trần Văn Việt | 117 | 10
DOCUMENT |  | 8
FrmDCdocuamentCentrer | DOCUMENT CENTER | View all report from report configuration | view by authorization | Hoàng Trung Hiếu | 92 | 9
|  | Choose report and condition to view template |  | Hoàng Trung Hiếu | 92 | 9
|  | Export data report with template choosed |  | Hoàng Trung Hiếu | 92 | 9
|  | Time sheet report |  | Hoàng Trung Hiếu | 101 | 19
|  | Evaluation report |  | Nguyễn Thị Huệ | 104 | 6
|  | Severance pay report |  | Nguyễn Thị Huệ | 110 | 6
|  | Insurance report |  | Nguyễn Thị Huệ | 116 | 5
|  | Salary/Bonus report |  | Lê Ngọc Tuấn | 104 | 20
Mobile Web |  | 10
FrmMLogin | LOGIN | Function login mobile |  | Đỗ Xuân Dũng | 46 | 8
|  | Change pass, forgot pass |  | Đỗ Xuân Dũng | 46 | 8
FrmHRTSabsent | ABSENCE REGISTER | Absent register |  | Đỗ Xuân Dũng | 54 | 10
|  | Review absent day |  | Đỗ Xuân Dũng | 54 | 10
|  | Absent remain |  | Đỗ Xuân Dũng | 54 | 10
FrmHRTSAttendance | ATTENDANCE REVIEW | Check in-out |  | Đỗ Xuân Dũng | 64 | 9
|  | Daily, monthly working time |  | Đỗ Xuân Dũng | 64 | 9
|  | Over time |  | Đỗ Xuân Dũng | 64 | 9
FrmHRPRsalary | SALARY CHECKING | Salary review |  | Đỗ Xuân Dũng | 73 | 6
FrmMNotification | NOTIFICATION | Policy, notification view |  | Đỗ Xuân Dũng | 79 | 6
EVALUATION |  | 17
FrmEVevaluationItem | EVALUATION ITEM | Add, update, delete items using on evaluation |  | Lê Ngọc Tuấn | 124 | 5
|  | Active , Inactive |  | Lê Ngọc Tuấn | 124 | 5
FrmEVevaluationType | EVALUAVTION TYPE | Add, update, delete type of evaluation | New contract, training,… | Lê Ngọc Tuấn | 129 | 5
|  | Active, Inactive |  | Lê Ngọc Tuấn | 129 | 5
FrmEVevaluationClass | EVALUATION CLASS | Add, update, delete CLASS using on evaluation |  | Đỗ Xuân Dũng | 85 | 5
|  | Active , Inactive |  | Đỗ Xuân Dũng | 85 | 5
FrmEVevaluationGrade | EVALUATION GRADE | Add, update, delete GRADE using on evaluation |  | Đỗ Xuân Dũng | 90 | 5
|  | Active , Inactive |  | Đỗ Xuân Dũng | 90 | 5
FrmEVevaluationconfiguration | EVALUATION CONFIGURATION | Choose type to configuration |  | Đỗ Xuân Dũng | 95 | 5
|  | Choose class on class list |  | Đỗ Xuân Dũng | 95 | 5
|  | Mapping to grade with score |  | Đỗ Xuân Dũng | 95 | 5
FrmEVevaluation | EVALUATION (NEW CONTRACT) | Choose class , department, month to review |  | Đỗ Xuân Dũng | 100 | 13
|  | List of item with configuration |  | Đỗ Xuân Dũng | 100 | 13
|  | Calculate to take result |  | Đỗ Xuân Dũng | 100 | 13
|  | Submit to save data |  | Đỗ Xuân Dũng | 100 | 13
|  | Confirm to fixed value |  | Đỗ Xuân Dũng | 100 | 13
|  | Approval to make the new contract |  | Đỗ Xuân Dũng | 100 | 13
SEVERANCE PAY |  | 11
FrmSEserveranceItem | SERVERANCE ITEM | Add, update, delete items using on evaluation |  | Hoàng Trung Hiếu | 120 | 5
|  | Active , Inactive |  | Hoàng Trung Hiếu | 120 | 5
FrmSEserveranceCondition | SERVERANCE CONDITION | Define condition link to item serverance |  | Hoàng Trung Hiếu | 125 | 5
|  | Set method to link data |  | Hoàng Trung Hiếu | 125 | 5
FrmSEserveranceFormulate | SERVERANCE FORMULATE | Add,update formulate to item serverance |  | Hoàng Trung Hiếu | 130 | 5
|  | Configuration formulate |  | Hoàng Trung Hiếu | 130 | 5
FrmSEserverancePay | SERVERANCE PAY | Review data for function |  | Nguyễn Thị Huệ | 121 | 12
|  | Calculate base on formulate |  | Nguyễn Thị Huệ | 121 | 12
|  | Choose or input value item |  | Nguyễn Thị Huệ | 121 | 12
|  | Save to apply result |  | Nguyễn Thị Huệ | 121 | 12
|  | Confirm to fixed value |  | Nguyễn Thị Huệ | 121 | 12
INSURANCE |  | 10
FrmINinsuranceTemplate | INSURANCE TEMPLATE | View template upload information on INSURANCE software |  | Đỗ Xuân Dũng | 113 | 4
|  | List of all employee with change information |  | Đỗ Xuân Dũng | 117 | 3
|  | List of employee with increase and decrease on month |  | Đỗ Xuân Dũng | 120 | 2
|  | Modify more information |  | Đỗ Xuân Dũng | 122 | 3
|  | Save data to apply |  | Đỗ Xuân Dũng | 125 | 3
|  | Export data report with template choosed |  | Đỗ Xuân Dũng | 128 | 7
FrmINTotalmonthly | TOTAL MONTHLY REPORT | View tempate report of total monthly pay |  | Nguyễn Duy Hưng | 112 | 6
|  | Export data report with template choosed |  | Nguyễn Duy Hưng | 112 | 6
FrmINdetailAmt | DETIAL AMOUNT BY MONTH | View list of data mount related insurance for employee and employer |  | Nguyễn Duy Hưng | 118 | 7
|  | Export data report with template choosed |  | Nguyễn Duy Hưng | 118 | 7
Final stages |  | 6
Korean tranaslate |  | Korean tranaslate | Ms.Kim Anh |  | 54 | 70
UI test |  | UI test | Mr.Loc |  | 26 | 100
Function test |  | Function test | Ms.Sri |  | 54 | 70
Logic test |  | Logic test |  | Nguyễn Duy Hưng | 124 | 10
Mobile Web test |  | Mobile Web test |  | Trần Văn Việt | 127 | 7
Cook book manual |  | Cook book manual | Ms.Sri |  | 124 | 12

## FUNCTIONS
MENU | SUB-MENU | FORM ID | FORM NAME | FUNCTIONS | DESCRIPTION | REMARK
CONFIGURATION | CATEGORY | FrmSYCcategory | CATEGORY | Insert, Update | Add or Update data
|  |  |  | Active, InActive, Dictionary | Don't using delete data, Add dictionary field
|  |  |  | Admin or User | Some category can be open for user
| DICTIONARY | FrmSYSDdictionary | DICTIONARY | Insert, Update | Add or Update data
|  |  |  | Active, InActive | Don't using delete data
|  |  |  | Admin or User | Some category can be open for user
|  |  |  | Menu, Form, Control | Apply for all title, control
| REPORT | FrmSYSRreport | REPORT CONFIG | Insert, Update | Add or Update data
|  |  |  | Configuration report name, link, dictionary, active, inactive, parameter | Configuration report
|  |  |  | Authorization | Authorization user
| USER | FrmSYUuser | USER | Insert, Update | Add or Update data
|  |  |  | Active, Inactive | Don't using delete data
|  |  |  | Role selected | Selected role
|  |  |  | Organization selected | Selected Organization
Company selected
| AUTHORIZATION | FrmSYAauthorization | AUTHORIZATION | Form selected
Insert, Update, Delete, Report, Export choose
H/R INFORMATION | H/R INFORMATION | FrmHRBbasicinfo | HR BASIC INFORMATION | Update personal info
Update work info
Add, Update certification
Add, Update family info
View, add, update discipline
View, add, update skill
Basic info history
Work history before join in
|  | FrmHROorganization | ORGANIZATION | Add, Update department
Active, Inactive note
Sort by view mode
|  | FrmHRCcompanyinfo | COMPANY INFO | Add, update company info
Data contract (labor contract print)
Print information (Report print)
|  | FrmHRWworkingstatus | OFFICIAL ORDER (WORKING STATUS) | Add, update working status
Confirm to update newest in Basic info.
Can not change data after confirmed
|  | FrmHRLlaborcontract | ENTER LABOR CONTRACT | Add, update labor contract
Confirm to update newest in Basic info.
Can not change data after confirmed
Print template by format (PDF, word)
|  | FrmHRLNextcontract | NEXT LABOR CONTRACT | Review current labor contract and Next labor contract
Edit to change data next contract and saving
Delete next contract info and make again information.
Transfer to labor contract table after saving
| DISCIPLINE | FrmHRDdisciplineinput | DISCIPLINE BATH INPUT | Show the list employee by department
Create data after fill out information and choose emp
Query result data
|  | FrmHRDdisciplineconf | DISCIPLINE CONFIGURATION | Add ,update, delete deduct of discipline condition
Select salary item (evalauation or salary table) by period
| SKILL | FrmHRSskillinput | SKILL BATH INPUT | Show the list employee by department
Create data after fill out information and choose emp
Query result data
|  | FrmHRSskillconf | SKILL CONFIGURATION | Add, update,delete condition skill result
Based on question test write down score
|  | FrmHRSskilltesting | SKILL TESTING | Select question combo and employee to test.
Allocation employee with test content => saving
Print template testing with question list
Input score test and get back result => skill result
Confirm to update empoyee skill
| RECUITMENT | FrmHRRrecruitmentrequest | RECRUITMENT REQUEST | Add, update plan reccuitment of each department
Query result with condition
|  | FrmHRRcandidateapply | CANDIDATE APPLY | Add, Update candidate information
Accept recruitment after pass test
Create employee ID after recruitment offer (add data on HR basic info)
|  | FrmHRRcandidateappointment | CANDIDATE APPOINTMENT | Query list of candidate by request
Select candidate and fill out date interview, place and saving.
Remove data and adding if something change
| TRAINING | FrmHRTtraningCourse | TRAINING COURSE REGISTER | Add, Update, delete source training
Set active, Inactive
|  | FrmHRTtrainingSelect | TRAINING SELECT | Select course
Update more detail course for training
Select list of employee to training
Save to apply
|  | FrmHRTtrainingResult | TRAINING RESULT | Choose sourse selected
Choose file path of scores emplyee
Upload to view on grid, User can be change scores again
Submit to save data
Click result to finished course
| VENDER MANAGEMENT | FrmHRVenderInfo | VENDER INFO. | Add, Update, Delete vender information
|  | FrmHRVNewEmpRegister | REGISTER NEW EMPLOYEE | Add, Update, Delete new employee of vender.
Create employee ID and transfer to HR basic information
| QUESTION | FrmHRQuestionCategory | QUESTION CATEGORY | Create structure question (hierarchy)
Base on question type make category ID and parent.
Active, inactive item using
|  | FrmHRQuestionInfo | QUESTION INFO. | Create list of question base on question category
Update, Delete function
Active, inactive item using
Query data result
|  | FrmHRQuestionSet | QUESTION SET | Query structure of category question and choose version
Add question on the structure question type
Remove question out structure
TIME SHEET | TIME SHEET STANDAR | FrmTSWorkTime | WORK TIME | Add, Update work time
Configuration on department, employee
|  | FrmTSTimeShift | TIME SHIFT | Add, Update shift using
Active, Inactive apply
|  | FrmTSHoliiday | HOLIDAY | Add, Update holiday
Configuration by department
| TIME SHEET PROCESS | FrmTSWorkshift | REGISTER WORK SHIFT | Register work shift for employee work diffirent in configuration
Option choose the date apply (case change date)
Can be more than 1 shift on day
Confirm data
|  | FrmTSAbsenceRegister | ABSENCE REGISTER | Register, update, delete absence by employee, department
Batch input data
Confirm data
|  |  |  | Open functions to apply in smartphone | APP
|  |  |  | Check absence status in smartphone | APP
|  | FrmTSDailyWorkConfirm | DAILY WORK CONFIRM | Log data finger to compare with shift and show result
Link to absence, holiday to daily work
Display work data with more than 1 shift
Show work data in case change date work
|  | FrmTSDailyWorkByPerson | DAILY WORK BY PERSON | Show on work recored of employee in month
Print template attendance by person on month
| OVER TIME | FrmTSOverTimeConfig | OVER TIME CONFIGURATION | Add, update time and kind of over time by shift | Using for auto
Confirm data
|  | FrmTSOverTimePlan | OVER TIME PLAN | Regitser OT plan for employee
Batch input data support
Accept function
|  | FrmTSOverTimeConfirm | OVER TIME CONFIRM | Base on daily work and OT plan or configuration, log OT data | If Plan > Actual, Actual, plan
Check one or more record
Confirm data
Link from OT plan, if not then link from configuration
| LEAVE MANAGEMENT | FrmTSLeaveConfiguration | LEAVE CONFIGURATION | Add condition for leave calculate with each kind of leave
Formula calculate remain leave
|  | FrmTSLeaveManagement | LEAVE MANAGEMENT | Show information employee with leave data.
|  |  |  | Display the used date and remain base on configuration | Already annual leave function
|  | FrmTSLeaveTransfer | LEAVE TRANSFER | Show all of leave result
|  |  |  | Check date remain and choose Pay type, Month to save | None, Payment, transfer
|  |  |  | Confirm data | Already annual leave function
| TIMESHEET CALCULATOR | FrmTSTimeSheetItem | TIMESHEET ITEM | Add, Update timesheet items
Choose option for absence, Over time,…
|  | FrmTSTimeSheetFormulated | TIMESHEET FORMULATED | Add configuration for formuated item
Option to change on future
|  | FrmTSTimeSheetResult | TIMESHEETRESULT | Function to calutate timesheet on month
Base on department and version salary
Confirm data
Function closing data
SALARY/BONUS | SALARY STANDARD | FrmPRsalaryVersion | SALARY VERSION | Add, Update salary version | Advance, salary, bonus
Add the department is condition
The period timesheet closing
|  | FrmPRsalaryTable | SALARY TABLE | Base on salary version make salary table by Job Code
Calculate on each step, level ,salary
Save to apply
|  | FrmPRsalaryItem | SALARY ITEMS | Create salary items for each type and resource to link data
|  |  |  | Condition to link data result | configuration, upload, input,…
Active, Inactive apply
|  | FrmPRcalculateMethod | CALCULATION METHOD | Choose item salary.Add, update condition to take amount
Set by amount, rate with period apply
|  | FrmPRsalaryFormulate | SALARY FORMULATED | Choose item salary.Add each formulated
View salary formulated total
| SALARY PROCESS | FrmPRAdvancePayment | ADVANCE PAYMENT | Query advance payment data
|  |  |  | Save advance payment data with kind and method | Mehtod: formulated or amount input
Confirm advance payment data
|  | FrmPREnterAllowance | ENTER ALLOWANCE | Add, update delete allowance by each employee | Insace some employee allowance not same in configuration
Query result
|  | FrmPRUploadPaymentData | UPLOAD PAYMENT DATA | Choose department, Item for query result.
Choose file path for upload data
Submit to save data
|  | FrmPRCalculatedSalary | CALCULATE SALARY | Choose department, version, month to calculate salary
Calculate function by department or person
Cancel function
Review data function click
| BONUS PROCESS | FrmPRbonusSetting | BONUS SETTING | Choose version, department to review data
Add, Update, Delete bonus condition
|  | FrmPRbonusCaculate | CALCULATE BONUS | Choose department, version, month to calculate bonus
Calculate function by department or person
Cancel function
Review data function click
| RESULT | FrmPRSalaryReport | SALARY REPORT | View result of salary calculate
Re-calculate for each employee
Closing salary data
|  | FrmPRBonusReport | BONUS REPORT | View result of bonus calculate
Adjust bonus data
Closing bonus data
Print bonus report
|  | FrmPRsalaryClosing | SALARY CLOSING | Choose department, month to closing
View history closing
|  | FrmPRSendPayslip | SEND PAYSLIP | View payslip data
|  |  |  | Choose function send payslip | Email, SMS
Show result send
DOCUMENT | DOCUMENT | FrmDCdocuamentCentrer | DOCUMENT CENTER | View all report from report configuration | view by authorization
Choose report and condition to view template
Export data report with template choosed
EVALUATION | EVALUATION STANDARD | FrmEVevaluationItem | EVALUATION ITEM | Add, update, delete items using on evaluation
Active , Inactive
|  | FrmEVevaluationType | EVALUAVTION TYPE | Add, update, delete type of evaluation | New contract, training,…
Active, Inactive
|  | FrmEVevaluationClass | EVALUATION CLASS | Add, update, delete CLASS using on evaluation
Active , Inactive
|  | FrmEVevaluationGrade | EVALUATION GRADE | Add, update, delete GRADE using on evaluation
Active , Inactive
| EVALUATION PROCESS | FrmEVevaluationconfiguration | EVALUATION CONFIGURATION | Choose type to configuration
Choose class on class list
Mapping to grade with score
|  | FrmEVevaluation | EVALUATION (NEW CONTRACT) | Choose class , department, month to review
List of item with configuration
Calculate to take result
Submit to save data
Confirm to fixed value
Approval to make the new contract
SEVERANCE PAY | SEVERANCE STANDARD | FrmSEserveranceItem | SERVERANCE ITEM | Add, update, delete items using on evaluation
Active , Inactive
|  | FrmSEserveranceCondition | SERVERANCE CONDITION | Define condition link to item serverance
Set method to link data
| SEVERANCE PROCESS | FrmSEserveranceFormulate | SERVERANCE FORMULATE | Add,update formulate to item serverance
Configuration formulate
|  | FrmSEserverancePay | SERVERANCE PAY | Review data for function
Calculate base on formulate
Choose or input value item
Save to apply result
Confirm to fixed value
INSURANCE | INSURANCE TEMPLATE | FrmINinsuranceTemplate | INSURANCE TEMPLATE | View template upload information on INSURANCE software
List of all employee with change information
List of employee with increase and decrease on month
Modify more information
Save data to apply
Export data report with template choosed
| INSURANCE REPORT | FrmINTotalmonthly | TOTAL MONTHLY REPORT | View tempate report of total monthly pay
Export data report with template choosed
|  | FrmINdetailAmt | DETIAL AMOUNT BY MONTH | View list of data mount related insurance for employee and employer
Export data report with template choosed

## HR Information
Detail process
REVIEWREV AND STRATEGIES AND REMUNERATION
TESTING
START
END
RECRUITMENT
SET PROBATION
HR INFO
WORK INFO
SALARY / BENEFIT
TRANSFER / ELIMINATE
RECRUITMENT PLAN
SET OFFICIAL
EVALUATION
SAVE CV
TRAINING
NEW POSITION REQUIRED
RECRUIT NEW PERSON
Yes
No
- For Position?
- For Department?
- How many in need?
Failed
Pass
Set probation period
Failed
Pass
End Probation Evaluation
- Employee ID / Alias
- Position
- Working History
- S/H Insurancance
Do I need to save this CV?
Do other department need this employee?
CONSIDER JOB ANALYSIS IS JOB DESCRIPTION
MOVE CURRENT EMP TO THE NEW POSITION
NEW CONTRACT?
Yes
No
SET GOALS AND PERFORMANCE EXPECTATION
UNDERTABLE TRAINING NEEDS ANALYSIS
TRAINING REQUIRE?
PLAN AND CONDUCT INDIVIDUAL OR GROUP TRAINING
Yes
MONITOR PERFORMANCE
No
SKILL ACHIEVEVED?
No
APPRAISE PERFORMANCE
SKILL
REVIEWREV AND STRATEGIES AND REMUNERATION
LABOR CONTRACT
ORGANIZATION
DESCRIPLINE REQUIRE?
DISCRIPLINE
Yes
Yes

## Organization
Company structure, unlimited level, authorization to smallest level,..
Organizational Module
Admin define the company's General Information (Common for all the branches)
Admin define the Corporation type and Classification in the organization
If User have permission to add/edit location, enter location details (Branch Name, Address, Tax Code, Corporation Type, Representative) Otherwise just search and view the locations
If User have permission to modify structure,enter department structure (level, classification, location and team members) Otherwise just view company's structure(Tree View)
If User have permission to modify property, enter property details and assignee Otherwise just search and view the property
<== BACK

## Discipline
Mr.Dung
Ms.Hue
<== BACK
Descripline description
Employee
Evaluation?
Violation Information Investigation
Evidence
Enter Violation Informations
Select Employees /By Department
Enough evidence to process ?
Violation Levels Configurations correspond Displine Decisions
Appreciate Violation Levels to Employee
Report
Report Daily, Weekly, Monthly, Yearly
System allows to make list by department.
Save Appreciation Results
Evaluation
Yes
Get descripline type
Input type of description
Penalty
Declare the penalty for each descripline type
Add configuration for using other function (evaluation, salary, allowance,....)
Report

## Labor contract
| Main function |  | Config for batch/auto system | Configuration
- New employee need to sign contract? |  |  |  |  | Contract Kind: Probation, Season, 1-n Years
- Old contract will expired soon? |  |  |  |  | Contract Type: Labor Contract, Appendix, Training Contract, Fullwage
- Employee just increase salary or change position? |  |  |  |  | Option to config: Period, Profile for each contract kind such as: department, employee, insurance or not, payment or not
Notice for contract renew/confirmation
Contract Duration, Date, Decide no, Number |  | Auto create next labor contract?
Salary, Insurance Salary,
Pospone or Terminate status, duration & reason
Official contract (for appendix only)
Signed by, signed at
Show data for only creator and user with higher permission
External payment, content, or planing for next labor contract
Able to notice to employee, via sms, email, push notification
START
END
START
END
Config for Batch Process
START
END
Config Labor Contract Items
In need to sign a contract with employee
Deal contract with employee
Input contract Info to system
Confirm/Approve contract info in system
Config for Salary Table
<== BACK

## Recruitment
Refer
<== BACK

## Official Order
Recruiment
Exists
No
Yes
Official Order input
Save History
Employee Info
Official Order
Official Order for employee
Other Decisions
Vender, customer,
outsourcing
<== BACK
START
END

## Skill
Chiến lược: Từ góc độ chiến lược, quản lý kỹ năng là sự kết hợp giữa kiến ​​thức và quản lý nhân sự (HR). Mục đích là để xác định các kỹ năng khác nhau cần thiết và các yêu cầu năng lực tương ứng. Điều này phải được dựa trên trọng tâm chiến lược. Có thể thiết lập các ưu tiên trong thời gian tốt để thúc đẩy sự phát triển lâu dài mong muốn của lực lượng lao động.
Chiến thuật: Quản lý kỹ năng chiến thuật là một câu chuyện hoàn toàn khác. Trưởng nhóm phải cung cấp đúng số lượng nhân viên phù hợp cho những ngày cần thiết. Khi tham khảo ý kiến ​​của bộ phận nhân sự, họ phải chăm sóc đào tạo và quy nạp.
Hoạt động: Là một phần của quản lý nghề nghiệp của họ, các cá nhân được đào tạo và phát triển theo yêu cầu của đội của họ.
LOẠI KỸ NĂNG QUẢN LÝ
1.KN KỸ THUẬT: QUÁ TRÌNH, KIẾN THỨC KỸ THUẬT, THÀNH THẠO. CÁC NHÀ QL SỬ DỤNG CÁC QUY TRÌNH, KỸ THUẬT & CÔNG CỤ CỦA 1 KHU VỰC CỤ THỂ
2.KN CON NGƯỜI: LIÊN QUAN CON NGƯỜI, KHẢ NĂNG TƯƠNG TÁC HIỆU QUẢ VỚI CON NGƯỜI
3.KN KHÁI NIỆM: THỰC HÀNH VỚI CÁC Ý TƯỞNG, HIỂU CÁC MỐI QUAN HỆ TRỪU TƯỢNG, PHÁT TRIỂN Ý TƯỞNG VÀ GIẢI QUYẾT VẤN ĐỀ 1 CÁCH SÁNG TẠO
Exists
Training
No
Test Skill
Employee Info
Yes
Pass
N
Yes
Allow Employee Skill
Report
Question list
START
END
Skill Information
<== BACK

## Vender-Cust-Out
Tách bảng (nhân viên,lương, công) hay không?
Exists
No
Yes
Vender/Cust Info input
Employee Info
Vender/Cust info
Department tree input
Time Attendance
Official Order
SALARY / BENEFIT
Stop Working
REPORT
<== BACK
START
END

## Training
<== BACK
Create Training Plan
Approval
Select Employees/By Departments
Check Courses To Training Plan
Exist?
Create Courses
No
Yes
Assign Courses To Training Plan
No
Yes
Trainning
Attendance
Enter Traing Result
Report
Report
Evaluation

## Question list
Question list Management
Admin
Define the question list for each purpose
Define the purpose using (evaluation, skill, training,…)
Configure question with purpose for template print
View all question with purpose using
Supervisor
View question with purpose using
View template question
Assign question template
HR staff
Registry question information
Upload question result of employee
View list of question of employee assign
Print template and report
New question
Exists
No
Yes
Question info input
Purpose
Question info
Question list
Print
Result upload
Templete
Yes
Report
No
<== BACK
START
END

## Time Sheet
START
END
Organization
Make work time
Make time shift
Make work shift
Employee
Time sheet item
Formula TS item
Absent register
Annual leave management
Holiday management
Absent?
No
Yes
Report
Over time?
No
Yes
Over Time
Daily work confirm
Report
Report

## Leave management
Holiday - National Holiday, … (labor law)
Absence Register - Page of vacation registration for each employee? Then HR confirm?
Annual Leave - Annual leave, transfer leaves, off, remaining leaves… The employee can be checked by themselves
Leave Management
Admin
Define the company holiday for each location (repeats annually)
Define the leave type (Annual, casual, medical) for each location and departments and whether it is carry over or not
Configure leave period (From 1st Jan - Dec 31)
Configure work week ( Specify weekends and workdays)
View all employee leave summary
Supervisor
View employee's leave summary in that department
View personal leave summary
View Department leave calendar
Assign leave for Department Employee
Approve / Reject leave
Apply leave
HR staff
View personal leave summary
Apply leave
<== BACK

## Daily work confirm
Config for time record device |  |  | Main function
- Device name, device type, event will get to use in system
- IP Address, Department: All dept or production, gate, security… only
- Only get data for In, Out, or Both
Config for formular
Such as: Time_in = min of today, Time_out = max of today
Worktime = Time_out - Time_in
<== BACK
START
Configuration for TimeRecord Device
END
START
Daily working time will be log by HR staff daily or auto
END
Collect data in time record device and set log for working time
Collect data absence register and set log for absence
Work time
device data
Collect data configuration for Working Time
Regiteration for Absence
Configuration for Worktime
Registeration for Workshift
Configuration for Workshift profile
Collect data Workshift register
(or auto detect workshift)
Calculate working time follow fomular
START
Config simply but detail steps about formular to calculate
END
Configuration for formular

## Time work shift
Main Function | Configuration
- Shift name & symbol
- Time in, out, break between shift, total hour?
- Time begin/end to calculate night shift
- Time start/end of finger data to detect workshift
- Create a new profile for configuring detail for employee postion…
- Config for Saturday/Sunday: halfday, fullday, full OT, off
- Config for Late and Soon, max time allowed?
- Config for Overtime when finish workshift: break time, ot from/to, min ot time, round ot time, need register or auto?
- Config for auto detect workshift
- allow to create a profile, include 1 or more workshift inside and allow to register by profile with option to repeat every week, 2 weeks…
- able to apply for employee work 2 shifts in a day if company have same request
- Create a new profile for configuring detail for department, employee
<== BACK
START
END
Input list of Workshift Items
Configuration detail for Workshift Items
Workshift Profile Setting for configuration very much detail
Workshift Profile Group
START
Register workshift profile for employee or department
END

## Formula TS Item
Exist?
No
Yes
Prepare Configuration Time Sheet
Choose Time Sheet Item to Configurate
Create new Time Sheet Item.
Call Function in Time Sheet Item Management
Choose Fomular for Time Sheet Item
Exist?
Define Fomular for this Time Sheet Item
No
Mapping The Time Sheet Item to Fomular.
Yes
Mapping Time Sheet Item with Fomular to ensure independence in Configuration
<== BACK

## OT Application
<== BACK
Approval
No
Yes
Prepares OT Request
Click OT Registered Function
Allow to register employee by department or upload from excel file
OT Report
+ Monthly OT Report
+ Weekly OT Report
+ Daily OT Report
Select Employees/ By Department
Enter OT Registered Informations
Call OT Function .
OverTime

## OverTime
Over time
Admin
Define over time plan
Define kind of over time with rate (150,200,….)
Configure over time (from time to time with rate…)
View all employee over time with period
Supervisor
View employee's over time summary or detail in that department
View personal over time with period
View Department over time
Approve / Reject over time
HR staff
View over time detial
Registry over time application
Check OT data with finger data
Apply over time
Confirmed?
No
Yes
Over time Confirm
<== BACK
Create over time request
Plan Over time request
Auto
Over time application
Over time configuation
Yes
Report
No
START
END
Caculator Overtime

## TimeSheet Item
<== BACK

## Work Time
<== BACK

## SALARY-BONUS
Timesheet checking
No
Yes
Report
END
START
All personal info correct
Payroll Cycle
- TIme attendance closes
- Over time closes
update correct personal info
Review completeness
- TIme attendance detial and total
- Over time data compare
Review & approve as needed
Timesheet closes
All employee report?
Contract employee who didn't report hours
Basic salary info
- Basic salary, allowance,....
- Check contract info, dependent person,....
Calculator
Salary table
Salary/Bonus item
Advance payment
Salary configuration
Bonus configuration
Upload payment data
Calculator Salary
Calculator Bonus
Report
No
Yes
salary
Bonus
Allowance

## Salary Bonus Item
No
Yes
- Condition value by Department / Duration / Employee / Month or Days / Job or Position…
- Condition setting: Range condition From - To / Rate or Amount
- Payment or Deduct
- Uploading or not / Display or not / Editable in salary report or not
START
END
In need to modify a Salary/Bonus Item
Set condition for the item
Set fomular and using for the item
Check exists
Create new Item
<== BACK

## Salary Bonus calculator
- If no one listed / Or Salary closed / Or Daily Working Data's not confirmed / Or no Contract duration avaiable
START
END
List employee avaiable to calculate salary/bonus this time
Init/Collect data setting for calculating
Check
Set Info of Labor Contracts / Allowance for each employee
Set info of Daily Working Time for each contract info
Calculate Working Day salary and OT Salary
Calculate Actual Salary
Calculate Actual amount of Allowance and Benefit
Calculate Payment and Deduct
Calculate Gross Salary
Calculate Insurance Amount and all Fees by Employee/Company
Calculate Taxable and Personal Income Tax
Adjust Benefit or Advance salary at final step of calculating
Calculate Net Income
Save Data
Review and Adjust manual amount if needed in salary Report
<== BACK

## Salary table
Overal pay range
Determine a company minimum and a company maximum pay. The minimum will be for the first and lowest grade and the maximum will be for the last and highest grade
A pay range will generally spread +/- 15-20% from the midpoint, but any range the employer feels is appropriate is acceptable, and ranges may be different for different grades.
For example, if your lowest paid position is an administrative assistant and you wish to pay at market, and salary survey data for that position shows an average salary of $25,000, a 15% spread for that job would be $21,250 (min), $25,000 (midpoint) and $28,750 (max), making $21,250 your overall minimum salary
Number of grades
the number of pay grades will depend on the size of your organization and the difference between the highest paid and lowest paid jobs.
Range per grade
Set a minimum and maximum for each grade. The maximum of one grade may overlap the minimum of another and vice versa. A common spread is +/- 15-20%, but it can be set at whatever the employer feels is acceptable
Grade chart
Using the sum of the minimum and the maximum, calculate the midpoint by simply dividing that sum by two ([Max + Min] / 2 = Midpoint).
Review and amend
Determine how often the pay grade will be reviewed and how often adjustments will be made. Annual salary and salary structure increase projections can be used to adjust as needed. Pay grades are typically reviewed every one to three years.
Over time
Admin
Create salary version
Create range group
View grade chart
Supervisor
Establish overall pay range
Establish number of grades
Establish a range per grade
View grade chart
Print report
HR staff
Create pay grade chart
Review and amend
Print report
Establish overall pay range
Establish number of grades
Establish a range per grade
Create pay grade chart
Review and amend
Create Version salary table
Create range group (position, department,...)
Version salary table
No
Yes
Exists?
Report
END
START
- Period to apply version (month or day???)
- Group apply version ??
- Step No, step level, salary
<== BACK
- Create table cinfiguration basic salary (position, personal,..)
- create table system for basic salary, basic allowance by item salary of each employee.

## Advance Payment
The monthly salary calculation varies by employee type:
Monthly employees: 40 percent of minimum wage.
Hourly employees: 40 percent of a 220-hour month at the hourly minimum wage.
Commission Employees: 40 percent of average commissions.
The system uses the following information when processing salary advances:
Employee HR information: Name, registration, hire date.
Time management information: Absences, vacations.
According to the Fair Labor Standards Act (FLSA)
The salary advance agreement => policy create and employee's agreeement => signatures
Agreement : how much money, deduct policy, contraint terminated
Advance payment
Admin
Define advance type
Define condition for policy
Configuration advance item formular
View all employee have eligible to advance
Supervisor
View employee's pay advance summary or detail in that department
View list of result calculator
Pay / Reject advance payment
HR staff
View condition advance detial
Check list of eligible for the advance
Calculator advance payment
View result report
Registry kind of advance
Defined the policy
END
START
Condition of each advance
Employee's agreement
Configuration advance item formular
Advance item
Exists?
Yes
No
Advance calculator
Employee info
Advance payment
Report
- Agree sign: condition pay advance, deduct policy, contraint terminated
- Period apply
- Time and attendance
- Leave condition ....
<== BACK
- Using salary formular for current working time (advance amount)

## Bonus Configuration
Advance payment
Admin
Registry bonus kind
Registry bonus condition
Configuration bonus item
View all employee have eligible to bonus
View bonus payment & report
Supervisor
View all employee have eligible to bonus
View list of result calculator
Pay / Reject advance payment
View report
HR staff
View condition bonus detial list of employee
Check list of eligible for the bonus
Calculator bonus
View result report
Bonus policy
Employee
Bonus kind
Bonus condition
Bonus item
END
START
PIT configuration
Configuration Bonus item
Calculator Bonus
Pay?
Bonus payment
Report
Yes
No
- Date join
- Time attendance
- Work kind
- Job code
- Department
....
- List of kind bonus follow policy company (labor international,13th salary,...)
- Times calculator PIT (Bonus, include salary...)
<== BACK

## Salary configuration
<== BACK

## Upload Payment Data
Salary/ Bonus | Upload payment data
Salary Item
END
START
Review
<== BACK
Upload?
Yes
No
Upload Payment

## Allowance
Salary/ Bonus | Allowance | Configuration allowance
Enter Allowance name
Select allowance condition type 1. Always True 2. Range 3. Custom Expression
Select allowance Computation type 1. Fixed amount 2. Percentage 3. Custom Definition
User can select whether the allowance is active or not
Manament allowance for employee for position, department,….??
Will be input allowance data on contract or separate form???
Incase 2 period allowance on one contract???
<== BACK

## EVALUATION
Evaluation policy
Evaluation item
END
START
Approval
Yes
No
- Evaluation for New Contract, Traning Course,probation contract ....
- setup field with configuration
- Authorization function, data view.
- Management result for next step
Group define
Organization
Final grade mapping
- Scale for grading by group, department,.....
- Group, deptcode, period, percent increase, final grade, scope point,..
- Class define (worker, line leader, staff, manager,...)
Evaluation type
- Type: New contract, training,...
- List item for each evaluation type and group.
Basic grade
Item grade mapping
- Mapping item with group using and list grade
Evaluation configuration
Evaluation Calculator
Employee
New contract
Update skill
Report

## Item
No
Yes
Prepare Information for Evaluation Item
Group Define
Edit Information of Item (Edit Item)
Exist?
Save Evaluation Item's Informations
(Save Item)
Enter Informations for Item (Add New Item)
Select Item Management Function
Select Item Group to Assign
Exist?
Yes
No
<== BACK

## Group Define
Evaluation policy
END
START
Exists
Yes
No
Input Group Evaluation
Evaluation item
Review
<== BACK
No
Yes
Prepare Information for Evaluation Group Definition
Edit Information of Group (Edit Group)
Exist?
Save Evaluation
Item's Informations
(Save Item)
Enter Informations for Group (Add New Group)
Select Group
Management Function

## Grade configuration
Evaluation policy
END
START
Exists
Yes
No
Basic grade
Grade mapping
Review
<== BACK
Evaluation Item
Final Grade mapping
Configuration

## Evaluation configuration
9491475
35092400
11724500
11270416.3333
<== BACK
Organization
END
START
Authorization?
Yes
No
Source link data
Review
Evaluation Type
Evaluation Item
- Descripline, Time sheet, absent,...
Destination link data
Item grade mapping
- Result of item when compare with item grade mapping
Setup formular
Authorization form
No
Yes
Report?
- Review, calculator, submit, approval,...
Report

## SEVERANCE PAY
Severance Pay | Items | List of Item using
Severance pay amount is based on the following factors
Length of employee's tenure with employer
Reason for termination (Employer downsizing, employee conduct or layoff)
Employers financial solvency
Severance pay policy should include
Situations when the policy will be applicable (downsize, layoff, changes in org. structure)
Situations when severance benefits are not applicable (misconduct)
Conditions when Periodic severance payment ends
Require employee to sign a waiver
Purpose of Severance pay benefits
Org reserves the right to alter or terminate the policy at its discretion
Severance pay items
1. Benefit amounts
2. Insurance benefits
3. Unemployment benefits
4. Outplacement services
5. Recommendation letters
6. Unused Vacation and Sick leave benefits
7. Equipment Benefits
Coverage and eligibility
Sign waiver to receive severance benefits
Limiting coverage when terminated due to economic reasons
Severance Items

## Condition configuration
No
Yes
Prepare for Condition Configuration
Exist?
Select Configuration Function
If Condition Configuration is not Existing. It means the first configuration for Condition Severance Pay
Select Company or Organization
Create Configuration
(Add New)
Edit Configuration
(Edit Form)
Edit Configuration when The Severance Pay Policy changs by Law.
Create Configuration when The first setup system.
Choise Company or Organization depend on location and countries policy.
Input Configuration Informations
Save Configuration Informations

## INSURANCE
Insurance
SI : Social Insurance
HI : Healthy Insurance
UI: Unemployment Insurance
- List of suggest increase, descrease employee with insurance (user choose date to update and data will be link to report)
- Insurance Payment (Template report will be import on Insurance system). Inherit salary calculator
- Collect all of Insurance report need and apply on HRM
Exist?
From Changes of Employee Information
Save Registered Insurance Inforamtions
(Update/Save Action)
Adjust Registered Insurance Informations
(Register Form/ Edit Action)
Export Registered Informations
Search Employee's Insurance Information Registration
(Search Form)
Register Employee's Insurance Information
(Register Form/ New Action)
Yes
No
Report data to support uploading them into Insurance System of supplier ( Step registerring Insurance from supplier.
Anny cases:
+ When Company has new Employee, to register New.
+ When Employee's information has changes, to adjust information.
Assign Ratios of Insurance Object:[Ratio of IS, HS,US]
(Register Form/ Edit Action)
Yes
Register Insurance Information
Exist?
Insurance Ratios Configuration
Report
(Monthly Report)

## Social_Insurance
Insurance | Social insurance | Number, increase, decrease,……
1. Select the country to define Social Insurance
2. Enter the policy percentage amount
3. Create report from Employee's database (Show number of Employees paid for Social Insurance, No. of new employees added this month, No. of old employees rejected this month)